LESSONS AND BEST PRACTICES HANDBOOK

Generative Artificial Intelligence Integration

Employing Accredited GenAI to Accelerate the Observation Life Cycle

in the Training Analysis and Feedback (TAF) Management Cell

84th Training Command  |  78th Training Division

Operation Sentinel Justice (OSJ) 2026  •  Camp Shelby, Mississippi

| Author | Lieutenant Colonel (LTC) Trey Waversak |
| --- | --- |
| AI-Integrations Cell | LTC Trey Waversak; Major (MAJ) Robert McDavid, Second-in-Command |
| Proponent | 84th Training Command Artificial Intelligence Integration Working Group |
| Authority | Commanding General, 78th Training Division; Commanding General, 84th Training Command |
| Version | 1.0 |
| Date | 18 June 2026 |

EXECUTIVE SUMMARY What OSJ 2026 Proved — and What Comes Next

The 78th Training Division has built, validated, and begun to scale an accredited generative artificial intelligence (GenAI) capability that materially accelerates the process by which every Rotational Training Unit (RTU) receives its training feedback. This handbook records both the results and the repeatable method behind them.

The problem. The observation life cycle that produces RTU feedback is document-driven and human-intensive, and it strains at two points — front-end observation development and the tail-end Tier 2 quality review at the TAF cell. A controlled exercise on 10 June 2026 showed the strain is structural, not a matter of effort: 39 analysts caught only 4.69 of 8 planted errors on first pass (about 59 percent), missed the most consequential technical errors most often, and showed almost no correlation between experience and accuracy (Pearson 0.24).

The response. The division fielded the Divisional Package on Ask Sage — the accredited IL5 / FedRAMP High platform — comprising three role-based personas (OCT, CHOT, TAF Analyst), a controlled prompt library, a shared data workspace, and standardized inputs, with guardrails embedded in every persona.

The results. Throughput modeling from the controlled baseline projects an approximate 97 percent reduction in TAF review-stage burden and a 58 percent reduction in end-to-end cycle time. Early live employment (N = 8, through 18 June) measured roughly 20 minutes of analyst hands-on time per full CTO — every product human-verified — an early, real reduction trending toward the modeled ceiling. The most important finding is quality: AI-assisted review catches the technical, low-salience defects humans miss, consistently and regardless of seniority. More than 400 personnel were trained or reached.

The broader opportunity. An enterprise automation review logged 19 recurring manual processes representing roughly 1,182 hours of labor per event — a conservative floor — with the TAF function alone accounting for about 1,038 of those hours, evidence that the case for accredited automation and AI extends well beyond the review bottleneck first solved.

The ask. Institutionalize the Divisional Package as a standing 78th TD product, resource enterprise licensing and tokens, and authorize a 12-to-24-month expansion across the 84th Training Command and the broader U.S. Army Reserve — with Phase 2 extending to SIPR, standing up a deliberate AI Integration Cadre, and instrumenting live measurement. The capability is proven, the toolkit is transferable, and the method is repeatable.

Foreword

This handbook captures observations, insights, and lessons from the integration of generative artificial intelligence (GenAI) into the Training Analysis and Feedback (TAF) Management Cell process across 84th Training Command and 78th Training Division exercises during fiscal years 2025 and 2026. It is written for the practitioners who plan, control, and assess these exercises, and it is intended to be used — and repeated — at every echelon that generates observations for our Rotational Training Units (RTUs).

The effort began as a practical response to a real bottleneck and grew, with the support of senior leaders and the command’s Artificial Intelligence Integration Working Group, into a repeatable practice. This document records both the results and the method, so that what worked here can be replicated elsewhere with confidence. The program is the work of the 78th TD AI-Integrations Cell — the author and Major (MAJ) Robert McDavid, who has served as its second-in-command since CSTX 2025 and who designed the practical exercise and report underpinning the findings herein.

TREY WAVERSAK

LTC, U.S. Army

78th TD AI-Integrations Cell

[ Command endorsement — to be added. ]

How to Read This Handbook

This product follows the conventions of the Army Lessons Learned Program and the Center for Army Lessons Learned (CALL). Three conventions run throughout:

- Observations, Insights, and Lessons (OIL).  Substantive points are framed as something observed, what it means, and what to do about it.

- DOTMLPF-P.  Lessons are tagged to one or more domains — doctrine, organization, training, materiel, leadership and education, personnel, facilities, and policy — so leaders can route them.

- Observation – Discussion – Recommendation (ODR).  Individual lessons follow this structure, mirroring the format already required of every JLLIS observation.

This handbook is a record of observations and best practices to inform employment. It does not replace or supersede doctrine, regulation, or command policy.

Contents

Executive Summary

Foreword

How to Read This Handbook

Introduction — Purpose, Scope, Problem / Demand Signal, Methodology

Chapter 1 — The Challenge

Chapter 2 — The Approach and Solution

Chapter 3 — Integration and Training

Chapter 4 — Execution: Observations, Insights, and Lessons

Chapter 5 — The Way Ahead

Summary of Lessons and Best Practices

Appendices

Appendix A — Generative AI Model and Platform Analysis

Appendix B — OSJ Practical Exercise Findings

Appendix C — Training Plan

Appendix D — Training Analysis and Feedback (TAF) Cell Playbook

Appendix E — Risk, Security, and Responsible Use

Appendix F — Acronyms and Glossary

Appendix G — Metrics Collection SOP  (published separately)

INTRODUCTION Purpose, Scope, and Method

Purpose

Intent. This handbook serves two linked purposes. First, it identifies and characterizes the generative artificial intelligence (GenAI) capabilities currently available within Department of War (DoW)-approved environments accredited at Impact Level 5 (IL5). Second, it documents how those capabilities are being integrated across the 84th Training Command and its subordinate formations, including the 78th Training Division, to build efficiencies, streamline protocols, and improve overall operational throughput and output.

Intended audience. The primary audience is the 84th Training Command and its subordinate units, to include the 78th Training Division. Within those formations, the handbook is written first for the practitioners who generate and refine exercise products: Observer-Controller/Trainers (OCTs); the Training Analysis and Feedback (TAF) Management Cell; Chief Observer-Controller/Trainers (CHOTs); Exercise Control (EXCON); and the higher, adjacent, lower, supporting, and supported (HALSS) elements.

Reader outcome. After using this handbook, the reader will be able to locate the accredited GenAI resources available to the command, employ those tools to streamline their workflows, build efficiencies into recurring tasks, and produce more impactful output.

Authority. This effort is conducted under the authority of the Commanding General, 78th Training Division, and the Commanding General, 84th Training Command, and is supported by the 84th Training Command Artificial Intelligence Integration Working Group.

Scope

This handbook draws on observations collected across multiple 84th Training Command and 78th Training Division exercises conducted during fiscal years 2025 and 2026. These include the Quartermaster Liquid Logistics Exercise (QLLEX) and the Command Staff Training Exercises (CSTX) of 2025 and 2026. The documented experience spans a range of operational objectives — sustainment, medical, combat support, and maneuver — observed across a wide variety of Rotational Training Units (RTUs).

Coverage extends from the division echelon down to the company level. Lessons are drawn from and written for the practitioners who plan, control, and assess these exercises, with emphasis on the OCTs, the TAF Management Cell, CHOTs, and EXCON.

This initial pilot is deliberately bounded. The following are out of scope for this phase:

- Classified systems.  SIPR and classified GenAI employment are not addressed in this phase; SIPR-level integration is a planned objective for Phase 2.

- HALSS integration.  HALSS is under consideration as an audience; owing to the SIPR restrictions above, its inclusion is on hold and scheduled for review in subsequent phases.

- Non-DoW-approved tools.  GenAI tools not accredited for Department of War use are excluded.

- Parallel efforts.  First Army (Active Component) initiatives under parallel development are not covered here.

This product is assessed as generally releasable to the public, with selected content designated Controlled Unclassified Information (CUI); portions are marked accordingly. The findings here do not replace or substitute for similar or parallel findings produced elsewhere, and they do not replace or supersede existing doctrine, regulation, or command policy.

Problem / Demand Signal

The catalyst for this effort was a specific, recurring friction point in OCT operations. On a brigade-level OCT team, eight to ten individual OCTs must consolidate their separate observations into a single, coherent product under tight time constraints. In May 2025, during QLLEX, then-Major (now Lieutenant Colonel) Trey Waversak recognized an opportunity to leverage GenAI to consolidate those multiple observations into one product and piloted the approach.

A second opportunity emerged at the TAF Management Cell. The TAF review-and-approval process occurs at the tail end of the exercise, where it routinely becomes a bottleneck under compressed timelines. GenAI offered a means to streamline that review and relieve the end-of-exercise crunch.

Realizing these opportunities surfaced several friction points the command had to work through: platform access on government systems; token limitations and replenishment; user buy-in and adoption; limited subject-matter expertise; product training; and senior-leader guidance.

The Reserve-Component training calendar sharpened each of these. Because the formations of the 78th Training Division are geographically dispersed, training had to be delivered at multiple home stations across the training year rather than in a single sitting. Onboarding users onto a central enterprise license likewise met initial hurdles. The support of the 84th Training Command Artificial Intelligence Integration Working Group proved decisive in overcoming these challenges and consolidating a unified user base.

As the division moves into larger-scale exercises such as OSJ, the cost of inaction compounds. Without an accredited, well-integrated GenAI capability, the command faces a TAF analyst cell operating beyond sustainable bandwidth and severely compressed time to refine the feedback delivered to training units at exercise culmination — with downstream effects on readiness at echelon. A further risk is structural: unaccredited commercial AI tools are already circulating in the force, and the window to establish a governed, accredited, measured alternative is finite. Early returns from the pilot were substantial; those results and the integration glide path are presented in the chapters that follow.

Methodology

Observations were collected through a direct, in-person practical exercise conducted on 10 June 2026, supplemented by live-employment data and timing and adoption measurements drawn from command training records. The practical exercise was preceded the prior day by Control School II, covering JLLIS observations and quality control. It was designed and produced, and its results captured and reported, by then-Captain (now Major) Robert McDavid of the 78th TD AI-Integrations Cell.

The Practical Exercise (Manual Baseline)

Thirty-nine TAF Analysts (ranks E6 through O5) each reviewed a single company-level JLLIS observation containing eight deliberate, scoreable errors, within a 20-minute time constraint. The exercise measured accuracy, time to completion, and the correlation of both with analyst experience, establishing the manual baseline against which Ask Sage persona-and-prompt assistance was assessed. Only the narrative sections were scored — Observation, Discussion, Recommendation, Implementation, and Event Description — not Administrative Data or the T&EO; the manual figures are therefore a conservative floor.

| Baseline measure (10 June 2026) | Result |
| --- | --- |
| Participants | 39 TAF Analysts (E6–O5) |
| Average analyst experience | 1.26 years |
| Average accuracy | 4.69 of 8 errors (~58.6% first-pass detection) |
| Average review time — unadjusted | 15.82 minutes (narrative only) |
| Average review time — time-adjusted | ~24.8 minutes (est.; accounts for time-capped analysts) |
| Perfect scores (8 of 8) | 4 analysts (10.3%) |
| Completed under 20 minutes | 22 analysts (56.4%) |
| Least-detected error types | Publication (30.8%); general (28.2%) |
| Experience–accuracy correlation | Weak (Pearson 0.24) |

TAF Analyst Throughput (Modeled)

Scaling the manual baseline against the OSJ population — 270 CTOs routed to the TAF cell — and pairing it with modeled AI-assisted processing time and a reduced return (kickback) rate yields the comparison below. The AI-assisted column reflects modeled machine-processing time within the review stage, not full analyst hands-on time, which is measured separately.

| Input | Manual | AI-Assisted (modeled) |
| --- | --- | --- |
| Average review time (min) | 15.82 | 0.05 |
| Total CTOs | 270 | 270 |
| Return (kickback) rate | 60% | 10% |
| Second reviews | 162 | 27 |
| First-pass review (min) | 4,271.4 | 13.5 |
| Second-pass review (min) | 2,562.8 | 1.35 |
| Setup and training (min) | 120 | 180 |
| Total review time (min) | 6,954.2 | 194.85 |
| In hours | 115.9 | 3.25 |
| Reduction | — | ~97% |

This yields an approximate 97 percent modeled improvement in TAF analyst throughput within the review stage — a modeled ceiling, not a measured analyst time.

End-to-End Cycle Time (Modeled)

The TAF review stage is only one segment of the full observation life cycle. Measured across all steps from OCT observation preparation through submission, the modeled cycle improves as follows:

| Step | Owner | Manual (min) | AI (min) |
| --- | --- | --- | --- |
| Observation Prep | OCT | 300 | 60 |
| Header Data | OCT | 20 | 20 |
| Task Matrix | OCT | 40 | 40 |
| Performance Matrix | OCT | 20 | 20 |
| Key Personnel | OCT | 10 | 10 |
| Tagging | CHOT | 15 | 15 |
| Initial Review | TAF | 15.82 | 0.5 |
| Secondary Review | TAF | 9.49 | 0.05 |
| Approval | TAF | 15 | 15 |
| Submission | — | 10 | 10 |
| Total (min) |  | 455.31 | 190.55 |
| In hours |  | 7.59 | 3.18 |
| Reduction |  | — | ~58% |

This yields an approximate 58 percent modeled improvement in end-to-end cycle time.

Reading the Figures Together

These measurements quantify different things and should not be conflated. The ~97 percent figure reflects the modeled throughput gain within the TAF review stage, where AI assistance is most concentrated. The ~58 percent figure reflects the modeled gain across the entire observation life cycle, in which several manual steps remain unchanged and therefore moderate the overall improvement. Both are modeled projections; the measured live result below is their empirical counterpart, and the three should be read as complementary, not interchangeable.

Measured Live Employment (through 18 June 2026)

Beyond the controlled baseline, the package was in live use during OSJ, and Total Hands-On Time was logged for completed CTOs. As of 18 June, the first eight complete entries (N = 8) averaged 20.4 minutes of analyst hands-on time per full CTO — approximately 4.8 minutes of AI interaction and 15.6 minutes of human verification. AI output graded 2 Ready, 4 Minor Edits, and 2 Not Ready; analysts materially modified the AI product in roughly 38 percent of reviews, evidence that outputs were critically reviewed rather than accepted wholesale. The two “Not Ready” outputs accounted for most logged kickbacks, identifying persona refinement as the highest-leverage quality improvement. Applied across the 270 CTOs against the time-adjusted manual baseline, this early-adoption average projects to roughly an 18 percent reduction — a measured figure expected to move toward the modeled ceiling as the persona matures and analyst proficiency increases.

Operational Stakes at OSJ Scale

Of the 297 CTOs scheduled for evaluation at OSJ, 27 are assigned to 1st Army, leaving 270 for the TAF team. At the observed manual average of 15.82 minutes per CTO, the total manual review burden is approximately 71.2 hours (and approximately 111.6 hours at the time-adjusted average). Distributed across the 58 available TAF Analysts, each would carry roughly 4.7 CTOs, or about 73.5 minutes of review time.

| OSJ workload (Assessment Tracking Tool, 10 JUN 26) | Value |
| --- | --- |
| CTOs scheduled for evaluation | 297 |
| CTOs assigned to 1st Army | 27 |
| CTOs routed to the TAF cell | 270 |
| TAF Analysts available | 58 |
| Total manual review burden | ~71.2 hrs (unadjusted) / ~111.6 hrs (adjusted) |
| Per-analyst load (manual) | ~4.7 CTOs / ~73.5 minutes |

Adoption and Utilization Data

Training and onboarding figures were drawn from command training records: more than 220 division staff were trained on the platform in the lead-up to the 2026 exercise season, with approximately 80 additional personnel trained during exercise execution (including Global Medic staff) and roughly 82 users onboarded onto the platform — more than 400 personnel trained or reached to date. Token-utilization records show 88 onboarded, actively consuming users during OSJ, drawing approximately 48 million tokens against the 84th Training Command enterprise allocation of 100 million. Consumption was concentrated: most users were light consumers (under ~400,000 inference tokens each), a small number were power users, and two “builder” accounts — responsible for the personas, prompt libraries, and datasets — each consumed upwards of two million tokens.

Limitations

- Data reflects a single division across a single training cycle and has not been validated across other divisions or commands.

- The pilot was designed and led by the author; observations were captured by the originating team.

- Manual review times were measured under a 20-minute cap; several analysts reached the cap, so the unadjusted baseline understates true manual burden (the ~24.8-minute adjusted figure bounds this).

- The baseline test case was a company-level observation, the most common echelon; review times for other echelons may differ.

- The modeled throughput and cycle-time figures isolate processing time; the live measured figure (N = 8) is an early-adoption snapshot that will mature as additional reviews are logged.

- Observation-preparation times are informed estimates rather than continuously measured values.

Source: OSJ 26 Assessment Tracking Tool, 10 JUN 26; TAF Quality Log (live employment, through 18 JUN 26). Complete per-analyst data and the eight planted errors are at Appendix B.

| CHAPTER 1 The Challenge |  |
| --- | --- |
| Bottom line. The observation life cycle that produces every RTU’s feedback is highly structured, document-driven, and human-intensive. Under exercise conditions it strains at two points — front-end preparation of observations and tail-end quality review at the TAF Management Cell — and a measured baseline shows that manual review is not only slow but lets a substantial share of errors through. These strains are the problem this handbook addresses. |  |

1.1  The Observation Life Cycle

The command assesses RTU performance through the TAF Management Cell process, executed in the Joint Lessons Learned Information System (JLLIS). Each observation moves through four custody stages — Draft, Pending, Active, and Validated — as it passes between roles:

- OC/T field work (Draft).  The Observer-Controller/Trainer observes the task, completes the Training and Evaluation Outline (T&EO), writes the cumulative written observation, uploads the T&EO, and submits to the CHOT.

- CHOT function (Pending).  The Chief Observer-Controller/Trainer opens pending observations, performs a Tier 1 Quality Control and Review (QCR), applies metadata tags, and advances the observation to Active.

- Analyst cell (Active → Validated).  The TAF Analyst opens active observations, performs a Tier 2 QCR, returns the observation for correction if required, and validates it once it meets standard.

- Linkage and delivery (Validated).  The analyst links validated observations and documents to the RTU’s JLLIS binder, building the Take Home Package (THP) that feeds the Final Exercise Report (FER).

The product the RTU ultimately receives — the THP and FER — is only as timely and as accurate as this pipeline allows. Every delay or defect upstream is inherited by the training audience downstream.

1.2  Where the Process Strains

Three strain points define the challenge. Each is stated below as an observation, with the affected DOTMLPF-P domains identified.

Strain 1 — Front-End Observation Development

Observation preparation by the OCT is the single largest time cost in the cycle. Building a complete, standard-compliant written observation — task performance summary, performance-measure ratings, narrative observation, discussion, and recommendation — requires roughly 300 minutes per observation under manual conditions. Across a brigade-level team of eight to ten OCTs, each producing observations for multiple CTOs, this consumes field time that could otherwise be spent observing and coaching the RTU.

DOTMLPF-P domains:  Training; Personnel

Strain 2 — Tail-End Tier 2 Quality Review

The Tier 2 QCR at the TAF cell concentrates at the tail end of the exercise, where it becomes a bottleneck under compressed change-of-mission and ENDEX timelines. The strain is magnified by a 60 percent return (kickback) rate under manual review: a majority of observations are sent back to the OCT for correction, generating a second wave of reviews precisely when time is shortest. At OSJ scale, the manual review of 270 CTOs at an average of 15.82 minutes each represents approximately 71.2 hours of work (about 111.6 hours at the adjusted average) distributed across 58 analysts — a substantial commitment at the busiest point of the exercise.

DOTMLPF-P domains:  Organization; Training; Personnel

Strain 3 — First-Pass Yield and Quality

The challenge is not only speed but accuracy. In the 10 June 2026 practical exercise, 39 TAF Analysts reviewed a company-level observation containing eight deliberate errors. On average, analysts identified only 4.69 of the 8 errors — a first-pass detection rate of approximately 59 percent — and only 4 of 39 (10.3 percent) achieved a perfect score. The least-detected errors were publication errors (caught by 30.8 percent) and general errors (28.2 percent). Notably, analyst experience correlated only weakly with accuracy (Pearson 0.24), meaning the command cannot rely on seasoning alone to close the quality gap. Manual review, in short, allows roughly two of every five planted errors to pass toward the RTU — a structural gap an AI standardizer is well suited to close.

DOTMLPF-P domains:  Training; Leadership and Education

1.3  Consequence at Echelon

These strains converge on the training audience. A THP or FER that arrives late, or that carries undetected errors, degrades the fidelity of the RTU’s readiness assessment and erodes the learning payoff at exercise culmination — the precise moment the feedback is most valuable. Because the senior trainer’s external evaluation and the unit’s readiness picture rest on validated observations, defects that survive the Tier 2 QCR can misrepresent unit performance and misdirect subsequent training. The cost of the bottleneck is therefore not measured in analyst hours alone, but in the quality of the assessment the Army places in the hands of its formations.

1.4  The Reserve-Component Multiplier

The Reserve-Component operating environment sharpens every strain above. The formations of the 78th Training Division are geographically dispersed, so cadre proficiency must be built and sustained across multiple home stations throughout the training year rather than in a single concentrated effort. Analyst experience is shallow and uneven — the practical-exercise population averaged 1.26 years in role — and, as noted, experience correlates only weakly with review accuracy. The result is a cell that must deliver consistent, high-quality output at exercise surge while operating with limited drill time, frequent turnover, and a thin bench of seasoned reviewers.

1.5  Framing the Opportunity

The same characteristics that make the observation life cycle burdensome also make it well suited to accredited GenAI assistance. The process is rule-based, document-centric, and governed by an explicit format — the JLLIS observation already requires an Observation, Discussion, and Recommendation, applies DOTMLPF-P, and follows fixed quality standards. These are precisely the conditions under which a tuned persona and prompt can accelerate drafting and sharpen review without displacing the judgment of the OCT, CHOT, or analyst. Chapter 2 describes the approach and the solution the command adopted to do so.

| CHAPTER 2 The Approach and Solution |  |
| --- | --- |
| Bottom line. The command’s response to the bottleneck was not a new process but a tool tuned to the existing one. The 78th Training Division adopted Ask Sage — the accredited IL5 GenAI platform — and built a Divisional Package of role-based personas and prompts that mirror the Army’s existing observation standard. The package accelerates drafting and review while leaving evaluation judgment with the human. |  |

2.1  The Capability: Ask Sage at IL5

Ask Sage is a secure, multimodal GenAI platform authorized at FedRAMP High and Department of War (DoW) IL5, available as an Army enterprise capability. Through a single accredited interface it provides access to multiple frontier large language models, allowing the user to select the best model for a given task.

Selection Rationale

At the time of the initial pilot, Ask Sage was the only DoW-approved generative AI platform available for employment. Other efforts were either pre-release or had been withdrawn from pilot — for example, GenAI.mil had not yet been released, and CamoGPT pilots had been pulled back. The command selected Ask Sage on that basis and has continued with it because it remains the most fully built-out IL5 platform for functionality and capability, surpassing other readily available IL5 options. A detailed platform comparison is at Appendix A.

Resolving the Token Limitation

Early employment during QLLEX encountered token (usage) limitations, which briefly required a fallback to another accredited tool. The 84th Training Command Artificial Intelligence Integration Working Group resolved this by establishing an unlimited-token process ahead of OSJ, removing a key barrier to scaled use.

2.2  Design Principle: Meet the Process Where It Lives

The central design choice was to mirror, not replace, the existing standard. Every JLLIS observation already requires an Observation, a Discussion, and a Recommendation; applies DOTMLPF-P; and follows fixed quality criteria. The Divisional Package was therefore built so that each AI persona produces output in the structure that OCTs and analysts already expect — Strengths, Weaknesses, and Recommendations for observations; the Army four-part format for after-action reviews; and doctrine-cited review for quality assurance. This lowered the adoption barrier: users were not learning a new product, they were accelerating a familiar one.

2.3  The Divisional Package

Developed on 1–2 February 2026 within the Divisional Ask Sage workspace, the package standardizes employment across three roles. It comprises role-based user personas, a prompt library, a shared data workspace, and standardized inputs — together designed to remove guesswork and produce consistent, complete outputs across users and rotations.

The Three Personas

Each persona fixes the model’s role, doctrinal grounding, output structure, and guardrails. The persona text is reproduced below.

Observer-Controller/Trainer (OCT) persona

System setup You are an Observer/Controller Trainer (OC/T) with the 78th Training Division, U.S. Army Reserve. You have deep expertise in Army doctrine (ADRP 7-0, ADP 6-22, FM 6-0), CATS-based METL evaluation, and observing training units (RTUs) including BCTs, Division HQs, sustainment units, and command staffs during EXEVALs and Warfighter exercises. Your writing is direct, factual, and observation-based. You assess unit performance against doctrinal standards and structure findings using Strengths, Weaknesses, and Recommendations (SWR). You do NOT assign T/P/U ratings. You do NOT include classified information. All content is UNCLASSIFIED.

Chief Observer-Controller/Trainer (CHOT) persona

System setup You are a Senior Observer/Controller Trainer serving as Chief of OC/T (CHOT) at the Colonel (O-6) level within the 78th Training Division, U.S. Army Reserve. You provide senior-level analysis, strategic synthesis, and executive-quality written products. Your writing is polished, precise, and appropriately critical. You draw on ADRP 7-0, CATS/METL frameworks, and extensive experience with BCT, Division, sustainment, and command staff evaluations during EXEVALs and Warfighter exercises. You synthesize OC/T observations into coherent senior assessments and prepare talking points for higher headquarters. You do NOT assign T/P/U ratings. You do NOT include classified information. All content is UNCLASSIFIED.

Training Analysis and Feedback (TAF) Analyst persona

System setup You are a TAF (Training Analysis and Feedback) Analyst with the 78th Training Division, U.S. Army Reserve. Your role is to review, quality-assure, and refine training assessment products submitted by OC/Ts and CHOTs. You evaluate products for: (1) accuracy and factual consistency, (2) completeness against required CATS/METL criteria, (3) proper formatting and professional military writing standards, (4) adherence to Army doctrine (ADRP 7-0, FM 6-0, ADP 6-22), and (5) appropriate tone for the intended audience. You provide specific, actionable feedback. You do NOT assign T/P/U ratings. All content is UNCLASSIFIED.

The Prompt Library, Workspace, and Inputs

Paired with the personas is a curated prompt library of task prompts organized by the three roles, each pairing a persona setup with a specific task prompt and a defined expected output. Employment follows a simple three-step method: paste the persona/system setup, paste the task prompt, and attach the completed observation or product (by drag-and-drop; the interface has no separate attach control); the model extracts unit, task, date, and context automatically. The library is maintained as a controlled, versioned reference. A shared Divisional data workspace and standardized input templates complete the package, ensuring that every user begins from the same baseline and produces output to the same standard.

The full prompt library is maintained as a controlled command reference and is not reproduced in this handbook. The persona text above is shown to illustrate design; the library itself is available through the 84th Training Command Artificial Intelligence Integration Working Group.

2.4  Use Cases Across the Observation Life Cycle

The package delivers value at the same points where Chapter 1 identified strain.

- Front end — OCT observation development.  Drafting structured observation write-ups, after-action reviews, hot-wash summaries, and METL-based readiness summaries, collapsing observation preparation from roughly 300 minutes toward approximately 60.

- Tail end — TAF Tier 2 quality review.  Comprehensive product quality review, doctrinal accuracy checks, completeness and CATS cross-walks, formatting review against the Army writing standard, classification scrubs, and a final approval checklist — the application measured on 10 June 2026.

- Senior synthesis — CHOT products.  Executive talking points, final after-action reviews, commander’s assessments, and strategic readiness narratives for higher headquarters.

2.5  Guardrails by Design

Guardrails are embedded in the personas themselves rather than bolted on after the fact:

- No readiness ratings.  Every persona is instructed never to assign Trained/Practiced/Untrained (T/P/U) ratings; that determination remains with the human evaluator.

- Unclassified, NIPR only.  All interactions are UNCLASSIFIED; no classified information, PII, or sensitive unit vulnerabilities are entered.

- Verify against doctrine.  Users verify all AI-generated products against current doctrine before submission.

- Human authority retained.  The OCT owns the observation, the analyst validates it, and the model serves as decision support — never decision authority.

DOTMLPF-P domains:  Materiel; Training; Leadership and Education; Policy

2.6  Bridge to Chapter 3

Having defined the capability and the package, the remaining question is how it was fielded and taught across a geographically dispersed Reserve-Component division. Chapter 3 documents the integration glide path — from the single-operator pilot at QLLEX to a standardized Divisional Package — and the tiered training that carried it to more than 400 personnel reached by the 2026 exercise season.

| CHAPTER 3 Integration and Training |  |
| --- | --- |
| Bottom line. The capability scaled because a single-operator experiment became a commander’s operational objective. A town-hall tasking from the 78th Training Division’s Commanding General converted exploration into a formal program, and a deliberate, home-station-by-home-station glide path — backed by senior leaders and supported by the 84th Training Command’s AI Integration Working Group — carried the Divisional Package from one user at QLLEX to more than 400 personnel reached. The decisive adoption lesson was simple: exposure and live demonstration overcame resistance that argument alone could not. |  |

3.1  The Integration Glide Path

Integration followed a deliberate crawl-walk-run progression across a single training year, drawn from the program’s own record.

| Event | Phase | Action | Significance |
| --- | --- | --- | --- |
| QLLEX, 31 May–14 Jun 25, Ft Dix | Initial pilot (single operator) | Compiled CHOT-team observations into JLLIS drafts using Ask Sage | Proof of concept |
| CSTX 2025 prep, 1–4 Aug 25, Ft McCoy | First formal training | Nine blocks of instruction over three days to OCTs, Analysts, TAF, and CHOTs | Formal program begins |
| 21 Sep 25, MS Teams | Broaden the base | Training extended to non-CSTX users on the monthly call | Wider exposure |
| 30–31 Jan 26, Ft Dix | Re-engagement (2.0) | 90-minute refresh, OSJ-specific FAQ, and the unlimited-token process | Token barrier removed |
| 1–2 Feb 26, Ft Dix | Divisional Package | Built the prompt library, data workspace, personas, and standardized inputs | Capability standardized |
| 2026 season (CSTX 2026 / OSJ) | Division-wide employment | Package employed at scale; more than 400 personnel reached | Operational at echelon |

3.2  The Pivot: From Exploration to Operational Objective

At QLLEX the effort was exploratory. Colonel (COL) Ken Whipkey, serving as the author’s Chief Observer-Controller/Trainer (CHOT), approved the use of the tools to see whether they would improve the team’s internal operational flow. The turning point came shortly afterward. Between QLLEX and CSTX 2025, the author presented the concept to Brigadier General (BG) Andrew Scarcella, Commanding General, 78th Training Division, during a town hall. BG Scarcella immediately tasked the author to build out the program, train the division, and put a formal program into motion.

That tasking was the definitive moment the effort shifted from exploratory to an operational objective. In preparation for CSTX 2025, COL Farabaugh carried the Commanding General’s support forward as one of the leading officers for the exercise. The author was subsequently invited into the 84th Training Command Artificial Intelligence Integration Working Group, led by COL Reno Fazio, which became the mechanism for enterprise licensing, token resolution, and a consolidated user base. The lesson is recorded at 3.5.

Forming the AI-Integrations Cell

The program also gained its second member at this point. Following one of the CSTX 2025 training sessions, then-Captain (now Major) Robert McDavid approached the author and volunteered to support the build-out, assisting with general user onboarding and basic platform training during CSTX 2025. He has served as the effort’s second-in-command since CSTX 2025. For OSJ 2026 he became part of the 78th TD AI-Integrations Cell — at that point a two-person team of the author and MAJ McDavid — and was integral to much of the training and to testing content. He designed and produced the practical exercise that captured the baseline measurements and prepared the report that documented them. MAJ McDavid remains one of the primary contributors to the program’s success.

3.3  The Training Approach

Training was hands-on and built around employing the personas and prompts against real products rather than abstract instruction, following the tiered crawl-walk-run model. The first formal delivery, 1–4 August 2025 at Fort McCoy, comprised nine blocks of instruction over three days to the full range of CSTX operators — OCTs, Analysts, the TAF Cell, and CHOTs — introducing GenAI concepts, the Ask Sage platform, input templates for OCT observation outputs, and TAF review workflows.

Subsequent touchpoints reinforced and broadened the base. A September 2025 session on the monthly training call extended instruction to non-CSTX participants. A January 2026 90-minute refresh updated users on new capabilities, fielded OSJ-specific questions, and introduced the unlimited-token process. Across these events the progression moved users from awareness, to supervised practitioner use on their own products, toward a small number of self-sufficient power users.

3.4  Scaling Across a Dispersed Division

The Reserve-Component operating environment shaped delivery. Because the formations of the 78th Training Division are geographically dispersed, training was delivered at multiple home stations across the training year rather than in a single concentrated effort. Onboarding users to a central enterprise license met initial hurdles; the 84th Training Command Artificial Intelligence Integration Working Group proved decisive in resolving licensing and token availability and in consolidating a unified user base.

By the 2026 exercise season, more than 220 division staff had been trained in the lead-up to CSTX 2026, approximately 80 additional personnel were trained during exercise execution (including Global Medic staff), and roughly 82 users were onboarded onto the platform — more than 400 personnel reached to date. The training and scaling load was carried by a two-person AI-Integrations Cell — the author and MAJ McDavid — supplemented by tech-savvy personnel and existing GenAI users identified ad hoc. A larger, deliberately resourced cadre was never established; that gap is addressed as a lesson at 3.5.

3.5  Observations and Lessons

The following integration lessons are stated in Observation–Discussion–Recommendation form and tagged to the affected DOTMLPF-P domains.

Lesson 3-1 — Senior-leader backing converts experiments into programs

Observation.  The initiative remained an individual experiment until the Commanding General personally tasked its build-out; from that point it was prioritized and resourced.

Discussion.  COL Whipkey’s approval enabled the QLLEX pilot, but it was BG Scarcella’s town-hall tasking, COL Farabaugh’s sponsorship at CSTX 2025, and entry into the 84th Working Group under COL Fazio that provided the authority, resourcing, and reach to scale across the division.

Recommendation.  Secure explicit senior-level tasking early, and pair the grassroots innovator with a senior sponsor who can resource licensing, direct attendance, and remove obstacles.

DOTMLPF-P domains:  Leadership and Education; Organization; Policy

Lesson 3-2 — Exposure overcomes resistance that argument cannot

Observation.  Two schools of resistance emerged: a principled objection that AI would dull officers’ skills or offload leader responsibility; and more seasoned, less tech-savvy personnel who were unfamiliar with or intimidated by the tools. In both cases, general exposure and live demonstration won cooperation.

Discussion.  The principled objection eased once users saw that the human retained judgment — no readiness ratings are assigned by the model, products are verified against doctrine, and the analyst still validates. The familiarity objection eased once users operated the tool themselves and saw immediate time savings on their own products.

Recommendation.  Lead with live demonstration on the audience’s own products rather than briefings; address the principled objectors with the human-in-the-loop guardrails and the less-familiar with hands-on keyboard time.

DOTMLPF-P domains:  Training; Leadership and Education; Personnel

Lesson 3-3 — Licensing and tokens are the long pole; resolve them first

Observation.  Token limitations forced a fallback to another tool during the QLLEX pilot and constrained early scaling, and onboarding to a central enterprise license met initial hurdles.

Discussion.  The 84th Working Group’s establishment of an unlimited-token process and a consolidated enterprise user base removed the single biggest practical barrier to adoption ahead of OSJ. A related gap surfaced at scale: the enterprise license did not include built-in retrieval-augmented (RAG) access to Army doctrinal libraries, and Tier 3 builders required administrative permissions to manage token allocation.

Recommendation.  Push for enterprise licensing, token allocation, RAG/dataset access, and builder-level admin permissions at the very outset, before training events begin, so that onboarding does not lag adoption and users practice on the same system they will employ.

DOTMLPF-P domains:  Materiel; Organization; Policy

Lesson 3-4 — Build the team of experts earlier

Observation.  The effort was carried by a two-person AI-Integrations Cell — the author and MAJ McDavid — supplemented by tech-savvy personnel identified ad hoc. A larger, deliberately resourced cadre was never stood up.

Discussion.  The two-person cell carried the program effectively, but its size concentrated dependence on a handful of people and slowed home-station delivery across dispersed formations. A deliberate, larger AI Integration Cadre, established earlier, would have distributed the training burden and reduced single-point dependence.

Recommendation.  Stand up a deliberate AI Integration Cadre at the outset — ideally one trained power user per brigade or major subordinate element — to scale training, sustain the capability, and reduce single-point dependence.

DOTMLPF-P domains:  Personnel; Organization; Training

Author’s assessment. Looking back across the glide path, the single change that would have accelerated the effort most was pushing harder and earlier for an enterprise license to onboard users ahead of the exercises. Establishing a deliberate team of experts sooner would have been the second. Beyond those two, the development and rollout proceeded about as well as could be expected given the limited resources, time, and prior exposure to these tools.

3.6  Bridge to Chapter 4

With the capability fielded and the division trained, the remaining question is how it performed under exercise conditions. Chapter 4 turns to execution at Operation Sentinel Justice — the observations, insights, and lessons from employing the Divisional Package at scale, and the measured results against the manual baseline.

| CHAPTER 4 Execution: Observations, Insights, and Lessons |  |
| --- | --- |
| Bottom line. At Operation Sentinel Justice the Divisional Package was employed across all three roles — OCTs developing CTOs, TAF analysts conducting Tier 2 review, and CHOTs producing senior synthesis — while a controlled practical exercise measured the manual baseline against AI-assisted review. Throughput modeling from that baseline projects an approximate 97 percent reduction in TAF review burden and 58 percent reduction in end-to-end cycle time; early live employment (N = 8) measured roughly 20 minutes of human-verified hands-on time per CTO, confirming real gains and trending toward the modeled ceiling. The sharpest gains are in quality, where manual review is weakest. |  |

4.1  Employment at OSJ

The division entered OSJ with more than 220 users pretrained in the concepts and employment of the package, and onboarded roughly 82 additional users on the ground at Camp Shelby, Mississippi. During Control School training, the AI-Integrations Cell conducted the practical exercise — designed and produced by MAJ McDavid — that also served as the baseline measurement event (see Methodology and Appendix B). From that point the package was employed at the levels established during planning: OCTs used Ask Sage to support CTO development, TAF analysts used the review persona for Tier 2 quality control, and CHOTs used the senior-synthesis personas for executive products. Employment matched the plan built over the preceding year.

Distinction for the reader: the throughput and cycle-time figures in this chapter are modeled projections derived from the controlled practical exercise of 10 June 2026. Live production employment ran in parallel; an initial measured snapshot (N = 8) is reported at 4.4, and full results will be concluded as the exercise continues and reported in a subsequent update.

4.2  The Modeled Case (from the Controlled Baseline)

The headline figures come from throughput modeling applied to the controlled practical exercise of 10 June 2026, in which 39 TAF analysts established a manual baseline that was then compared against AI-assisted review. Against that baseline, and scaled to the OSJ population of 270 CTOs, the comparison yields:

- TAF analyst throughput: an approximate 97 percent modeled reduction in total review burden (see the Methodology throughput table).

- End-to-end cycle time: an approximate 58 percent modeled reduction across the full observation life cycle (see the Methodology end-to-end table).

These figures derive from the controlled comparison and throughput model rather than from independent instrumentation of all 270 live CTOs. The live employment running in parallel is realizing real gains, reported next, with full results concluded as the exercise continues.

4.3  The Quality Finding

Speed is only half the value; the more consequential finding concerns quality. In the controlled exercise, analysts identified only 4.69 of 8 planted errors under manual review — a first-pass detection rate of roughly 59 percent. The errors most often missed were the technical and least apparent ones: publication errors (caught by 30.8 percent of analysts) and general errors (28.2 percent), while the more obvious grammar and positive-opinion errors were caught most often (56.4 percent). Analyst experience correlated only weakly with accuracy (Pearson 0.24).

The implication is significant. AI-assisted review adds the most value precisely where human reviewers are weakest — the technical, low-salience defects that slip past manual quality control — and it does so consistently, independent of analyst seniority. The capability’s core contribution is therefore as much about first-pass yield and product quality as it is about time saved.

Figure 1.  Manual first-pass detection by error type (OSJ 2026, N = 39). The most consequential errors were the least detected.

4.4  Live Employment: Measured Snapshot and Indications

Beyond the controlled measurement, the package was in live use across the exercise, and analyst hands-on time was logged. Through 18 June, the first eight complete AI-assisted reviews (N = 8) averaged 20.4 minutes of analyst hands-on time per full CTO — about 4.8 minutes of AI interaction and 15.6 minutes of human verification. AI output graded 2 Ready, 4 Minor Edits, and 2 Not Ready, and analysts materially modified the product in roughly 38 percent of reviews — confirming that outputs were critically reviewed, not accepted wholesale. Against the time-adjusted manual baseline, this early-adoption average corresponds to roughly an 18 percent reduction, a measured floor expected to deepen toward the modeled ceiling as personas mature and proficiency grows.

Qualitatively, initial results exceeded expectations on quality: the AI quality checks caught exactly the kinds of defects intended, manual CTO generation time is being reduced, and unit review time is being reduced as expected. The two “Not Ready” outputs in the sample drove most kickbacks and pinpoint persona refinement as the highest-leverage next improvement. No notable failures, breakdowns, or limitations occurred in employment.

The only notable limitations were platform-level. As Ask Sage moved into the exercise, certain usability features — notably native support for shared personas and prompt libraries — were not fully built out, requiring manual workarounds to distribute the Divisional Package. These were known deficiencies going into the exercise and did not impede employment. Full live results will be concluded as the exercise continues.

4.5  Observations, Insights, and Lessons

The following execution lessons are stated in Observation–Discussion–Recommendation form and tagged to the affected DOTMLPF-P domains.

Lesson 4-1 — Adoption follows a fixed readiness pipeline

Observation.  The capability arrived at the exercise ready because four things happened in order: enterprise licensing, user onboarding, initial concept training, and then in-depth tactical employment training.

Discussion.  Each step is a precondition for the next. Onboarding without a license stalls; training without onboarding is theoretical; and exercise employment without prior training overwhelms users at the worst possible moment. The ordered sequence — not any single step — produced more than 220 ready users at the start of the exercise.

Recommendation.  Treat the four steps as a non-negotiable, ordered pipeline and resource them in sequence well ahead of the exercise. See also Lesson 3-3 on resolving licensing and tokens first.

DOTMLPF-P domains:  Organization; Training; Materiel; Policy

Lesson 4-2 — The decisive value is quality, not merely speed

Observation.  Manual review missed roughly 41 percent of planted errors and was weakest on technical, low-salience defects; AI-assisted review caught them consistently, independent of analyst experience.

Discussion.  A program sold only on time savings undersells itself and invites the “AI dulls our skills” objection. The stronger, defensible case is that AI raises first-pass yield on exactly the errors humans miss, while the human retains judgment and the readiness-rating authority.

Recommendation.  Frame and measure the capability on quality and first-pass yield alongside time saved, and lead engagements with the error-detection finding rather than the time figure alone.

DOTMLPF-P domains:  Training; Leadership and Education

Lesson 4-3 — Platform maturity can lag the concept; plan workarounds

Observation.  As the platform moved into the exercise, native support for shared personas and prompt libraries was not fully built out, requiring manual distribution of the Divisional Package; built-in RAG access to doctrinal libraries was likewise unavailable on the enterprise license.

Discussion.  The concept outran the platform’s native sharing and retrieval features. This did not stop employment, but it added friction and concentrated dependence on the package’s author for distribution.

Recommendation.  Identify platform feature gaps early; build manual distribution workarounds such as controlled reference documents and standardized copy-paste packages; and feed requirements — native sharing and RAG access — back to the vendor through the 84th Working Group.

DOTMLPF-P domains:  Materiel; Organization

Lesson 4-4 — Instrument live employment, not only the controlled case

Observation.  The headline metrics are modeled from a controlled practical exercise; live production employment was instrumented only as an early snapshot (N = 8), not across all CTOs.

Discussion.  The controlled baseline is rigorous and defensible, and the early live snapshot is encouraging, but neither is the same as fully measured production. Validating the modeled findings against real exercise conditions at scale strengthens the case and surfaces effects a controlled test cannot.

Recommendation.  Design measurement into the next exercise so that live CTO production yields its own throughput, return-rate, and quality data, validating the modeled case at scale (see the Metrics Collection SOP, Appendix G).

DOTMLPF-P domains:  Training; Organization

4.6  Bridge to Chapter 5

The modeled case is strong, the early live measurement is encouraging, and employment is tracking to expectation — yet the effort remains a single division’s experience captured at one exercise. Chapter 5 turns to the way ahead: the repeatable methodology that allows any unit to stand up this capability the same way, the broader automation opportunity the program has surfaced, and the path to scale beyond the 78th Training Division.

| CHAPTER 5 The Way Ahead |  |
| --- | --- |
| Bottom line. The value of this effort is not the single success at OSJ but the repeatable method behind it. Any division or brigade-level staff can stand up the same capability by running a fixed cycle — assess, license, onboard, train, employ, measure, refine, replicate — and by inheriting a transferable toolkit of personas, prompts, training, and SOPs. With command approval and funding, the program can scale across the 84th Training Command and the broader U.S. Army Reserve, expand to additional accredited tools, and extend from NIPR to SIPR. The path forward is innovation, employed with discipline and integrity. |  |

5.1  The Repeatable Methodology

The effort is designed to be run again, the same way, by any unit. The rinse-and-repeat cycle formalizes the readiness pipeline proven at OSJ into a transferable, ordered sequence. Each step is a precondition for the next; run in order, the cycle removes guesswork.

| Step | Action |
| --- | --- |
| 1. Assess | Identify the unit’s highest-payoff use cases; baseline current timelines and product quality. |
| 2. License | Secure enterprise licensing and token allocation first (Lesson 3-3). |
| 3. Onboard | Provision accounts and access to the accredited platform. |
| 4. Train | Deliver tiered training from awareness through hands-on practitioner and power-user blocks. |
| 5. Employ | Put the package to work across OCTs, the TAF cell, and CHOTs during the exercise. |
| 6. Measure | Capture throughput and quality data against a baseline (see Methodology and Appendix B). |
| 7. Refine | Update personas, prompts, training, and SOPs from observed results. |
| 8. Replicate | Hand the proven package to the next unit and repeat. |

5.2  The Resource Toolkit

Replication does not start from zero. The transferable package a receiving unit inherits comprises:

- The three role-based personas (OCT, CHOT, and TAF analyst).

- The prompt library and standardized inputs.

- The shared data workspace and data libraries.

- The tiered training blocks and an accompanying training schedule.

- The measurement design — the baseline test case and the metrics.

- The governing standard operating procedures.

Together these allow a new unit to reach employment in a fraction of the time the originating effort required.

5.3  The Path to Scale

Within the next 12 to 24 months, the objective is a fully approved and funded program that any division or brigade-level staff can adopt — complete with license funding, a training-plan schedule, and the resource toolkit. The realistic ceiling is availability across at least the 84th Training Command and the broader U.S. Army Reserve Command (USARC).

Adoption signals support that ambition. On the ground at OSJ 2026, interest was overwhelmingly positive, with many personnel actively requesting additional training and support — demand pulling the capability forward rather than command pushing it.

Resourcing the expansion will turn on token economics as much as licensing. OSJ consumed approximately 48 million tokens against the 84th Training Command’s 100-million-token enterprise allocation — roughly half the command-wide cap for a single division’s single exercise. Consumption is concentrated in a small number of builder accounts, which is favorable for scaling; but a single division’s burn rate indicates the allocation will require review as additional divisions and exercises come online, and Tier 3 builders should hold administrative permissions to manage allocation across the enterprise. The dollar cost of the license and token bank is held at the enterprise/CDAO level and is required to build a defensible cost model for the expansion.

The capability set should also broaden. Beyond Ask Sage, there is potential to incorporate additional accredited tools — for example, Anthropic’s Claude and more intuitive platforms such as NotebookLM or Context AI — and to pursue application-programming-interface (API) plug-ins, integration with Microsoft Teams, and deeper integration with existing Army systems. A comparative analysis of leading platforms is at Appendix A. Any such expansion remains subject to the same non-negotiable condition that governed this effort: a tool must be DoW-accredited at the appropriate impact level before it is employed.

5.4  The Broader Automation Opportunity

Beyond accelerating the observation life cycle, the program surfaced a broader opportunity. The OSJ Manual Task Automation Tracker logged 19 distinct recurring manual processes across the training enterprise, representing approximately 1,182 hours of recurring labor per event and 9 high-priority automation opportunities. The TAF function alone accounted for 15 of the 19 processes (about 1,038 hours) and 7 of the 9 high-priority opportunities. The highest-time processes carried the strongest automation scores:

| High-time TAF process | Recurring labor / event |
| --- | --- |
| Multi-step JLLIS quality-control review | 14,400 minutes |
| Daily update briefing compilation | 12,600 minutes |
| Automated deadline reminders | 8,400 minutes |

Automation and AI are distinct, complementary opportunities. Much of the logged burden is automation — file routing, naming-convention enforcement, PDF conversion, and dashboard tracking — rather than generative AI per se. Recurring TAF deliverables (the C2T2 memo, Unit Deficiency Certificate, CTO memo, storyboards, STUB Deck / Quad Charts, and the take home packet) originate from RTU-sourced data and follow a predictable, repeatable production cycle, yet must be managed simultaneously across individual OC/T folders, TAF shared folders, and RTU-facing directories — creating version-mismatch risk and coordination overhead. An automated pipeline that routes products to the correct folders on completion, flags non-standard submissions, and maintains a centralized tracking dashboard would return analyst time to observation quality and feedback.

These figures are a conservative floor. Only four OC/T processes were logged, and none from EXCON, HALSS, or Effects & Enablers, owing to data-collection time and personnel constraints; enterprise-wide automation potential is therefore understated and warrants deeper follow-on analysis. The detailed tracker and per-process scoring are maintained as Block 5 of the Metrics Collection SOP (Appendix G).

5.5  Phase 2: From NIPR to SIPR and Capability Expansion

A Secret Internet Protocol Router (SIPR) network build-out should be a close follower to the NIPR effort, extending the capability to classified work. Accessing those systems carries real hurdles and limitations that must be worked deliberately, but the expansion is worth pursuing; the intent is to field the capability across both NIPR and SIPR. Phase 2 also encompasses the platform-maturity fixes identified in Chapter 4 — native sharing of personas and prompt libraries, and RAG access to doctrinal libraries — the stand-up of a deliberate AI Integration Cadre (Lesson 3-4), and the live-employment instrumentation recommended in Lesson 4-4.

5.6  Sustainment and Institutionalization

For the capability to endure, it must become a standing product rather than one officer’s initiative. Internally, across the 78th Training Division, the personas, training, products, prompts, libraries, SOPs, and data libraries should be institutionalized as formal divisional references. Beyond the 78th, the goal is broader: not merely to distribute finished products, but to give units and organizations the ability to build their own. Sustainment rests on a deliberate AI Integration Cadre, version control of personas and prompts, governance through the 84th Working Group, and periodic refresh as models and doctrine evolve.

5.7  Closing — A Call to Responsible Innovation

This handbook documents one division’s path from a single-operator experiment to a measured, scalable capability. The invitation to sister divisions is straightforward: approach these advanced capabilities with an open and responsible mindset. Like any tool, their value depends on the discipline and integrity of the user who employs them — the human remains responsible for judgment, accuracy, and the readiness-rating authority that no model assumes.

Employed that way, the advantage these capabilities provide is a step-change beyond the incremental gains of recent years. It should not be discounted for the sake of preserving traditional mechanisms. Innovation, employed responsibly, is the path forward.

SUMMARY Lessons and Best Practices

This page consolidates the eight lessons developed across Chapters 3 and 4 into a single reference. Each lesson is stated as a recommended action and tagged to the affected DOTMLPF-P domains, so leaders can scan, prioritize, and route them. The full Observation–Discussion–Recommendation entries appear in the chapters indicated.

| # | Lesson and recommended action | DOTMLPF-P |
| --- | --- | --- |
| 3-1 | Senior-leader backing converts experiments into programs. Secure explicit senior tasking early and pair the innovator with a senior sponsor who can resource licensing, direct attendance, and remove obstacles. | Leadership & Education; Organization; Policy |
| 3-2 | Exposure overcomes resistance that argument cannot. Lead with live demonstration on the audience’s own products; address principled objectors with the human-in-the-loop guardrails and the less-familiar with hands-on time. | Training; Leadership & Education; Personnel |
| 3-3 | Licensing and tokens are the long pole. Push for enterprise licensing, token allocation, RAG access, and builder admin permissions at the very outset, before training events begin. | Materiel; Organization; Policy |
| 3-4 | Build the team of experts earlier. Stand up a deliberate AI Integration Cadre at the outset — ideally one trained power user per brigade or major subordinate element. | Personnel; Organization; Training |
| 4-1 | Adoption follows a fixed readiness pipeline. Run license, onboard, train, then employ in order; each step is a precondition for the next. | Organization; Training; Materiel; Policy |
| 4-2 | The decisive value is quality, not merely speed. Frame and measure on first-pass yield alongside time saved, and lead engagements with the error-detection finding. | Training; Leadership & Education |
| 4-3 | Platform maturity can lag the concept. Identify feature gaps early, build manual distribution workarounds, and feed requirements (native sharing, RAG access) back through the 84th Working Group. | Materiel; Organization |
| 4-4 | Instrument live employment, not only the controlled case. Design measurement into the next exercise so live production yields its own throughput, return-rate, and quality data. | Training; Organization |

Where to focus. Across the eight lessons, the Organization and Training domains recur most often, followed by Materiel and Leadership and Education. A unit replicating this effort should concentrate first on the organizational preconditions — licensing, the readiness pipeline, and a deliberate AI Integration Cadre — and on hands-on, demonstration-led training, as these underwrite every other gain.

Appendices A through F follow this summary. The Metrics Collection SOP is published separately as Appendix G.

APPENDIX A Generative AI Model and Platform Analysis

This appendix reproduces the 78th Training Division’s platform analysis (LTC Trey Waversak and MAJ Robert McDavid, 8 June 2026), comparing three generative AI platforms across capability, availability, and cost. It is the evidence base for the selection rationale at Chapter 2 and the future-tools path at Chapter 5.

A.1  Purpose and Method

The analysis evaluates three platforms — Ask Sage, GenAI.mil (Gemini), and Claude Opus 4.8 — across three categories: Model Intelligence, User Tool Availability, and Cost. Each feature was scored on a 0-to-5 scale, where 0 represents a complete absence of functionality and 5 denotes best-in-class performance. Claude was included as a best-in-class benchmark for complex processing even though it is not currently accredited for DoW use or available within GenAI.mil. Should an accredited environment integrate such a model, the findings and weightings could shift significantly.

A.2  Weighted Scoring

| Feature | Ask Sage | GenAI.mil | Claude |
| --- | --- | --- | --- |
| LLM Breadth | 5 | 1 | 3 |
| Model Intellect | 4 | 2 | 5 |
| RAG / Internet | 3 | 3 | 3 |
| Data Cloud | 4 | 1 | 3 |
| Shared Workspace | 4 | 0 | 4 |
| Prompt Library | 3 | 0 | 4 |
| Custom Skills / Persona | 4 | 0 | 5 |
| Multimodal Input | 2 | 2 | 4 |
| Multimodal Output | 1 | 2 | 4 |
| Vibe Coding | 0 | 0 | 4 |
| Security / Compliance | 5 | 5 | 1 |
| Token Usage | 2 | 5 | 3 |
| Onboarding | 2 | 5 | 3 |
| Ease of Use | 3 | 5 | 4 |
| Prompt Criticality | 3 | 2 | 4 |
| Total | 45 | 33 | 54 |

A.3  Interpretation

Claude leads overall on total functionality and versatility, scoring highest in model intellect, custom skills and personas, multimodal capability, and collaborative features. Ask Sage performs strongly in LLM breadth, security and compliance, and collaborative tools, making it a robust option for secure, broad application. GenAI.mil excels in security and compliance, token usage, onboarding, and ease of use, but lags in advanced features and customization.

A.4  Platform Profiles

| Platform | Where it excels | Where it lacks |
| --- | --- | --- |
| Ask Sage | Broad access to many premier LLMs; workbook sharing, prompt library, personas, and data-cloud tools; IL5-approved. | Token-heavy with high cost and replenishment demands; requires an enterprise license; tenant navigation; data-cloud tuning consumes training tokens quickly. |
| GenAI.mil (Gemini) | Easy onboarding and access for CAC holders; pooled, effectively unlimited token usage; familiar and easy for novice users. | Limited to a single LLM (Gemini); lacks shared workspace or shared products; very limited input/output (chat only). |
| Claude | Best-in-class LLM intellect; robust range of shared-space tools; multimodal input and output. | Not currently IL5-accredited or available within GenAI.mil; complex models can be token-heavy; token costs not yet known. |

A.5  Conclusion

Among accredited options, Ask Sage currently offers DoW members the most robust and collaborative capability, despite higher costs and onboarding hurdles. GenAI.mil remains limited to basic chat but excels in security and free token access. Claude is the most capable platform evaluated, but present barriers — chiefly the lack of IL5 accreditation and availability within GenAI.mil — prevent its adoption. Were an accredited environment such as GenAI.mil to integrate a Claude-class model, it could surpass Ask Sage by combining advanced functionality with secure, cost-effective access. This reinforces the selection rationale at Chapter 2 and the future-tools path at Chapter 5.

Scores reflect platform capabilities as assessed on 8 June 2026 and will evolve as platforms mature and accreditation changes.

APPENDIX B OSJ Practical Exercise Findings

This appendix presents the full results of the controlled practical exercise conducted on 10 June 2026 during OSJ Control School training, designed and produced by then-Captain (now Major) Robert McDavid of the 78th TD AI-Integrations Cell. It established the manual baseline used throughout this handbook.

B.1  Design

Thirty-nine TAF Analysts, ranks E6 through O5, each reviewed a single company-level JLLIS observation containing eight deliberate, scoreable errors, within a 20-minute time constraint. The exercise measured accuracy, time to completion, and the correlation of both with analyst experience.

B.2  Summary Statistics

| Measure | Result |
| --- | --- |
| Participants | 39 TAF Analysts (E6–O5) |
| Average experience | 1.26 years |
| Average accuracy | 4.69 of 8 errors (~58.6%) |
| Average review time (unadjusted) | 15.82 minutes |
| Average review time (time-adjusted) | ~24.8 minutes (est.) |
| Perfect scores (8 of 8) | 4 analysts (10.3%) |
| Scored 3–6 errors | 29 analysts (74.4%) |
| Completed under 20 minutes | 22 analysts (56.4%) |
| Reached the 20-minute cap | 17 analysts (43.6%) |
| Fastest perfect score | Soldier 18 — 4.0 yrs experience, 9.0 minutes |
| Experience–accuracy correlation | Pearson 0.24 (weak) |

B.3  Error-Type Detection Rates

Detection varied sharply by error type. The most apparent errors were caught most often; the technical and least apparent errors were missed most often (see Figure 1, Chapter 4).

| Error type | Analysts detecting | Rate |
| --- | --- | --- |
| Grammar | 22 of 39 | 56.4% |
| Positive opinion statement | 22 of 39 | 56.4% |
| Date | 17 of 39 | 43.6% |
| Opinion statements (other) | 14–17 of 39 | 35.9–43.6% |
| Publication | 12 of 39 | 30.8% |
| General | 11 of 39 | 28.2% |

B.4  The Eight Planted Errors

| Error type | Description |
| --- | --- |
| Date | “2035” listed in place of “2025” (incorrect year). |
| Publication | Does not cite the Army Regulation number nor paragraph/line (missing required reference and citation). |
| Abbreviation | “Unit Movement Officer” not abbreviated/handled per standard. |
| Opinion | “We think…” (inappropriate use of opinion language). |
| Opinion | “Without an alternate UMO, the company is practically guaranteed to fail its next mission due to catastrophic logistical breakdowns” (unsubstantiated opinion). |
| Opinion | “OCT Team thinks…” (inappropriate use of opinion language). |
| Grammar | “we’re” used in place of “were” (incorrect word usage). |
| Opinion | “They did a….” (incomplete/unclear opinion statement). |

B.5  OSJ Workload — CTOs by Echelon

The OSJ assessment population comprised 270 CTOs routed to the TAF cell, distributed across echelons as follows. (The company level — the most common echelon — was the baseline test case.)

| BDE |  | BN | CO | GRP | TM | Other |
| --- | --- | --- | --- | --- | --- | --- |
| 13 |  | 81 | 93 | 14 | 44 | 25 |
| “Other” comprises CMD (3), DET (6), OFF (3), PLT (9), SEC (3), and TA (1). Source: OSJ 26 Assessment Tracking Tool, 10 JUN 26. |  |  |  |  |  |  |

B.6  Per-Analyst Data

The complete dataset for all 39 participants follows. Time is capped at 20 minutes; analysts marked at 20 may have required additional time.

| Soldier | Experience (yrs) | Total correct (of 8) | Time (min) |
| --- | --- | --- | --- |
| 1 | 1 | 8 | 20 |
| 2 | 1 | 8 | 20 |
| 3 | 1 | 3 | 20 |
| 4 | 1 | 7 | 20 |
| 5 | 2 | 8 | 10 |
| 6 | 1 | 6 | 20 |
| 7 | 2 | 6 | 20 |
| 8 | 1 | 4 | 20 |
| 9 | 1 | 5 | 15 |
| 10 | 2 | 4 | 20 |
| 11 | 1 | 7 | 13 |
| 12 | 1 | 4 | 18 |
| 13 | 1 | 6 | 20 |
| 14 | 1 | 1 | 20 |
| 15 | 1 | 3 | 16 |
| 16 | 1 | 3 | 16 |
| 17 | 1 | 3 | 20 |
| 18 | 4 | 8 | 9 |
| 19 | 1 | 5 | 20 |
| 20 | 1 | 5 | 20 |
| 21 | 1 | 5 | 14 |
| 22 | 1 | 5 | 19 |
| 23 | 1 | 4 | 20 |
| 24 | 1 | 5 | 13 |
| 25 | 1 | 0 | 5 |
| 26 | 1 | 4 | 11 |
| 27 | 1 | 5 | 10 |
| 28 | 2 | 5 | 13 |
| 29 | 1 | 6 | 8 |
| 30 | 3 | 3 | 7 |
| 31 | 1 | 7 | 11 |
| 32 | 1 | 5 | 15 |
| 33 | 1 | 5 | 11 |
| 34 | 2 | 5 | 20 |
| 35 | 1 | 2 | 20 |
| 36 | 1 | 4 | 20 |
| 37 | 1 | 3 | 18 |
| 38 | 1 | 3 | 18 |
| 39 | 1 | 3 | 7 |

Averages: experience 1.26 years; total correct 4.69 of 8; time 15.82 minutes.

APPENDIX C Training Plan

This training plan operationalizes the tiered model described in the body of the handbook and the glide path proven across 2025–2026. It is hands-on and use-case-driven, sequenced crawl-walk-run, and scaled to a notional exercise in June 2027. Durations and dates in brackets are planning placeholders to be set against the command training calendar.

C.1  Tiered Programs of Instruction

| Tier | Topics | Length | Outcome |
| --- | --- | --- | --- |
| Tier 1 — Awareness | Platform overview; authorization boundary (IL5/NIPR); responsible use; basic prompting | [ 1–2 hr ] | Personnel can access the tool and use it safely for simple tasks. |
| Tier 2 — Practitioner | Persona/prompt workflows; document analysis; verification discipline; the three-step method | [ 0.5–1 day ] | OCTs, analysts, and CHOTs apply the package to real products with review. |
| Tier 3 — Power User | Custom datasets and retrieval; persona and prompt-library curation; mentoring | [ 1–2 days ] | Champions build and maintain the package and mentor their cells. |
| Tier 4 — Trainer | Instructional delivery of Tiers 1–3; sustainment and governance | [ As required ] | Cadre sustain and replicate the program independently. |

C.2  Notional Schedule toward a June 2027 Exercise

The schedule mirrors the proven glide path, phased backward from exercise execution so that licensing, onboarding, and training precede employment in the correct order (see Lesson 4-1).

| Timeframe | Event | Focus |
| --- | --- | --- |
| [ ~Sep 2026 ] | License and access | Confirm enterprise licensing and token allocation; provision accounts (resolve the long pole first). |
| [ ~Oct–Nov 2026 ] | Tier 1 awareness (division-wide) | Broad exposure via home-station sessions and monthly calls; responsible-use briefing. |
| [ ~Dec 2026–Jan 2027 ] | Tier 3 cadre development | Train one power user per brigade or major subordinate element; stand up the AI Integration Cadre. |
| [ ~Feb–Mar 2027 ] | Tier 2 practitioner (role-based) | Hands-on persona/prompt employment for OCTs, analysts, and CHOTs on real products. |
| [ ~Apr–May 2027 ] | Refresh and rehearsal | Updates, exercise-specific FAQ, package rehearsal, and a baseline measurement event. |
| [ Jun 2027 ] | Exercise employment | Full employment across the observation life cycle; live measurement and after-action capture. |

C.3  Resources, Prerequisites, and Assessment

- Resources: accredited accounts, the Divisional Package (personas, prompt library, data workspace, inputs), and a short student handbook.

- Prerequisites: completed Tier 1 and acknowledgment of the responsible-use guidance at Appendix E.

- Assessment: a practical exercise per tier; Tier 3 requires building or maintaining a working persona and dataset; Tier 4 requires a teach-back.

Bracketed dates and durations are planning placeholders; set final values against the command training calendar.

APPENDIX D TAF Cell Playbook (Summary)

The Training Analysis and Feedback (TAF) Cell Playbook is the companion reference that defines the cell whose process this handbook accelerates. It is summarized here; the controlled version (V3) is maintained by the 78th Training Division. The playbook is marked UNCLASSIFIED // FOR OFFICIAL USE ONLY and references AR 350-1, FM 7-0, TC 25-10, and the 78th Training Division Exercise SOP.

D.1  Mission and Core Functions

The TAF Cell provides analytical and administrative support to the OCT mission before, during, and after exercises, enabling effective feedback and improved unit readiness through comprehensive AARs and Take Home Packages. Its core functions are:

- Data collection and management — operate observation tracking systems; receive, log, and organize OCT inputs.

- Analytical support — synthesize observations into trends aligned to the training unit’s METL.

- AAR support — prepare materials, visual aids, and timelines for AARs at all echelons.

- Take Home Package development — compile, quality-check, and deliver post-exercise documentation.

- OCT coordination — serve as the information hub synchronizing observation and feedback across OCT teams.

D.2  Key Positions

| Position | Key responsibilities |
| --- | --- |
| OIC / NCOIC | Overall leadership; coordinates with exercise control, OCT leadership, and the training unit; sets priorities and battle rhythm; quality-controls all products. |
| Data Manager | Operates and maintains tracking systems (e.g., JLLIS); ensures data integrity; manages access. |
| Analyst(s) | Reviews and synthesizes observation data; identifies trends by warfighting function; drafts analytical summaries; supports METL crosswalk. |
| AAR Coordinator | Develops AAR schedules; prepares slide decks, timelines, and graphics; manages AAR logistics. |
| THP Compiler | Consolidates data, observations, and products into the final Take Home Package; executes quality review before delivery. |
| Communications / Battle Tracker | Maintains situational awareness; tracks the exercise timeline and significant events; ensures information flow. |

D.3  Boundaries — What the TAF Cell Is and Is Not

| The TAF Cell IS… |  | The TAF Cell IS NOT… |
| --- | --- | --- |
| A supporting element for the OCT mission |  | The Exercise Design Cell — it does not build the scenario, orders, or architecture |
| The data collection and management hub for observations |  | The HALSS cell — it does not manage simulations, models, or role players |
| The primary producer of AAR support materials |  | An evaluation authority — it supports OCTs who evaluate; it does not rate units |
| The assembler and quality controller of the Take Home Package |  | A replacement for the training unit’s staff |
| A coordinator and synchronizer between OCT teams |  | The exercise control group (EXCON) — it does not inject or control exercise flow |
| A provider of analytical summaries and trend analysis |  | An intelligence or operations cell — it analyzes training data, not simulated tactical intelligence |
| This is a summary. The complete TAF Cell Playbook (V3) is maintained as a controlled command reference and should be attached to this handbook in full at publication. |  |  |

APPENDIX E Risk, Security, and Responsible Use

This appendix consolidates the guardrails that govern employment of the capability. They are embedded in the personas themselves and reinforced here as command guidance. The overriding principle is that generative AI is decision support, never decision authority; the human retains judgment and the readiness-rating authority.

E.1  Core Principles

- Human in the loop. The OCT owns the observation, the analyst validates it, and no model assigns a T/P/U rating.

- Verify before use. Confirm facts, figures, citations, and doctrinal references against current doctrine before submission.

- Respect the boundary. Operate only within the accredited environment; this effort is bounded to IL5, NIPR, and UNCLASSIFIED content.

- Protect information. Do not enter classified information, PII, or sensitive unit vulnerabilities into the platform.

E.2  Classification and Data-Handling Rules

All AI interactions in this phase are UNCLASSIFIED and conducted on NIPR. Users apply standard operations-security (OPSEC) review to inputs and outputs, use generalized descriptions where specificity would breach classification, and route any product requiring a higher level through the appropriate accredited channel. SIPR and classified employment are out of scope until accredited (see Chapter 5, Phase 2).

E.3  Risks and Mitigations

| Risk | Mitigation |
| --- | --- |
| Fabrication or inaccuracy | Persona constraints, retrieval grounding, and mandatory human verification against doctrine before submission. |
| Over-reliance / skill erosion | Employ AI as augmentation only; the human retains judgment and the rating authority; preserve manual proficiency in training. |
| Classification or PII spillage | UNCLASSIFIED/NIPR-only rule; classification-and-sensitivity scrub persona; OPSEC review of inputs and outputs. |
| Inconsistent or biased output | Standardized personas and inputs; analyst Tier 2 review; doctrine-cited quality checks. |
| Shadow use of unaccredited tools | Field an accredited alternative (Ask Sage at IL5); publish clear guidance; lead by demonstration. |
| Platform or version drift | Version-control personas and prompts; periodic refresh as models and doctrine evolve; governance through the 84th Working Group. |

E.4  Prohibited and Restricted Uses

- No entry of classified information, PII, or sensitive vulnerabilities into the platform.

- No use of unaccredited commercial GenAI tools for official products.

- No assignment of T/P/U ratings by the model; that determination remains a human responsibility.

- No release of an AI-assisted product without human review, verification, and approval.

| APPENDIX F Acronyms and Glossary |  |
| --- | --- |
| Acronym | Meaning |
| AAR | After-Action Review |
| API | Application Programming Interface |
| ATIS | Army Training Information System |
| ATN | Army Training Network |
| CATS | Combined Arms Training Strategy |
| CHOT | Chief Observer-Controller/Trainer |
| CTO | Command Training Objective |
| CSTX | Command Staff Training Exercise |
| CUI | Controlled Unclassified Information |
| DOTMLPF-P | Doctrine, Organization, Training, Materiel, Leadership and Education, Personnel, Facilities, and Policy |
| DoW | Department of War |
| EXCON | Exercise Control |
| FedRAMP | Federal Risk and Authorization Management Program |
| FER | Final Exercise Report |
| GenAI | Generative Artificial Intelligence |
| HALSS | Higher, Adjacent, Lower, Supporting, and Supported |
| IL5 / IL6 | Impact Level 5 / Impact Level 6 |
| JLLIS | Joint Lessons Learned Information System |
| LLM | Large Language Model |
| METL | Mission Essential Task List |
| NIPR | Non-classified Internet Protocol Router (network) |
| OCT | Observer-Controller/Trainer |
| OSJ | Operation Sentinel Justice |
| PII | Personally Identifiable Information |
| QCR | Quality Control and Review |
| QLLEX | Quartermaster Liquid Logistics Exercise |
| RAG | Retrieval-Augmented Generation |
| RTU | Rotational Training Unit |
| SIPR | Secret Internet Protocol Router (network) |
| SOP | Standard Operating Procedure |
| SWR | Strengths, Weaknesses, and Recommendations |
| TAF | Training Analysis and Feedback (Cell) |
| T&EO | Training and Evaluation Outline |
| THP | Take Home Package |
| T/P/U | Trained / Practiced / Untrained (readiness rating) |
| USARC | United States Army Reserve Command |