S3 TRAINING OFFICER FIELD GUIDE Rolling Out Generative AI at the Battalion A TPU Battle-Assembly Playbook • 78th TD AI-Integrations Cell • 18 June 2026

BE SURE TO — What this is. A run-with-it playbook for the battalion S3 / Training Officer to field the division’s generative AI (GenAI) capability — the Ask Sage Divisional Package — across a Troop Program Unit (TPU) training year. It is built around battle assemblies (BAs), not consecutive duty days. Follow it in order, use the checklists, and heed the callouts. The objective: your OCTs, CHOTs, and analysts arrive at Annual Training (AT) trained, onboarded, and ready to employ.

1.  The Bottom Line for the S3

You own the rollout plan, the training calendar, and the readiness of your cell. The capability is proven; your job is to get people licensed, onboarded, trained, and employing it on real products before AT. Four things make or break it, in this order: licenses and tokens, leader top-cover, hands-on demonstration, and a couple of trained champions who are not you. Sequence them right and the rest follows.

WATCH OUT — The long pole is access, not training. Licensing and token allocation take the longest and block everything downstream. Start the request at BA-1, not when training begins. If you wait, you will train people who cannot log in.

BE SURE TO — Treat this like a T/P/U gate. Put GenAI onboarding and training tasks on your battle-assembly schedule as trackable items with a Trained / Practiced / Untrained status per Soldier, just like any other individual task.

2.  The 12-Month TPU Rollout Timeline

Phased backward from AT / the exercise so that access precedes training and training precedes employment. Compress or stretch to fit your unit’s battle rhythm; the order does not change.

| Battle Assembly | Objective | S3 actions |
| --- | --- | --- |
| BA-1 (~12 mo out) | Secure access (the long pole) | Submit enterprise license / token request through higher and the 84th AI Working Group; identify your champion(s); nominate your cell roster (OCTs, CHOTs, analysts). |
| BA-2 | Leader top-cover & messaging | Brief the commander; get the rollout on the training guidance; pre-empt resistance with a live demo at officer/NCO huddle. |
| BA-3 | AI Integration Cadre development | Train 1–2 power users (not just yourself) on personas, prompts, and the data workspace; assign them as trainers for later BAs. |
| BA-4 | Tier 1 awareness (everyone) | Account provisioning check; 60–90 min hands-on intro for the whole cell; responsible-use brief; verify everyone can log in. |
| BA-5 | Tier 2 practitioner (role-based) | OCTs practice observation drafting; analysts practice Tier 2 review; CHOTs practice synthesis — all on real or realistic products. |
| BA-6 | Rehearsal & dry run | Run a mock observation through the full cycle (OCT → CHOT → analyst); time it; fix friction; refresh accounts/tokens. |
| AT / Exercise | Employ & measure | Full employment across the cycle; capture time and quality data; collect after-action notes for the next iteration. |

WATCH OUT — Drill-weekend amnesia is real. A 30-day gap between BAs erases unpracticed skills. End every BA with a one-page “what we did / what is next” so users restart fast, and put a 10-minute refresher at the top of each session.

3.  Training Blocks, Sized for a Battle Assembly

Each block fits inside drill time and is hands-on. Do not lecture; put hands on keyboards against real products.

| Block | Time | Content and outcome |
| --- | --- | --- |
| Tier 1 Awareness | 60–90 min | Platform login, authorization boundary (IL5 / NIPR / UNCLASSIFIED), responsible use, basic prompting, the three-step method (persona → task prompt → attach document). Note: the Ask Sage interface has no file-attach button — attach by drag-and-drop. Outcome: everyone can log in and run a simple task safely. |
| Tier 2 Practitioner | Half day | Role-based persona/prompt workflows on real products; verification against doctrine; the kickback/return loop. Outcome: OCTs, analysts, and CHOTs produce a real product with supervision. |
| Tier 3 Champion | 1–2 BAs | Persona and prompt-library upkeep, custom datasets, and teaching others. Outcome: 1–2 self-sufficient trainers who carry the load when you are pulled away. |

BE SURE TO — Train the role, not the tool. OCTs care about faster, cleaner observations; analysts care about catching errors; CHOTs care about senior products. Frame each block around the user’s job, and they buy in.

4.  Per-Battle-Assembly Checklists

Access & Accounts (start at BA-1)

- License/token request submitted through higher and the 84th AI Working Group.

- Cell roster nominated and de-conflicted with unit MTOE/assignments.

- Accounts provisioned; every user has logged in once and reset as needed.

- RAG / dataset access confirmed (Army pubs, TDPs, TNEOs). The 84th enterprise license did not include built-in database access at OSJ — request it explicitly if your workflows need it.

- Replenishment / unlimited-token process confirmed, with a named requester on the ground, before AT.

Token planning factors (for the BA-1 request).

Consumption is concentrated: a few builders generate most of the load, while the bulk of the cell is light. Use these planning factors, drawn from OSJ 2026, to size the request. Your training tiers map to consumption tiers — awareness users are light consumers; champions are the heavy builders.

| Tier | Typical token use | Note |
| --- | --- | --- |
| Tier 1 — Consumer | Under ~400K inference; limited training | The large majority of your cell (routine chat, review, look-ups). |
| Tier 2 — Power user | Higher inference + training | A handful; uploads source files and uses chat heavily. |
| Tier 3 — Builder/Champion | ~2M+ each | 1–2 per unit; builds personas, prompts, and datasets. |

Benchmark: OSJ 2026 consumed ~48M tokens across 88 active users in a single exercise (the 84th TC enterprise license cap is 100M). Plan your request against your headcount and the number of exercises you will support.

People & Buy-In

- Commander briefed; rollout on the published training guidance.

- Champion(s) identified and trained ahead of the force.

- Live demonstration delivered to the skeptics on their own products.

Training Execution

- Tier 1 delivered to the whole cell; logins verified.

- Tier 2 delivered by role on real products.

- Full-cycle dry run timed and friction logged.

Readiness for AT

- Personas, prompt library, and inputs distributed and current.

- Responsible-use guidance acknowledged by all users.

- Refresh and token check completed at the BA before AT.

5.  Watch-Outs and Best Practices

These are the challenges, constraints, and bottlenecks we have already hit. Plan around them.

WATCH OUT — Tokens run out mid-exercise. Tuning and heavy use burn tokens fast. Confirm the replenishment/unlimited process is active before AT, and name who can request more on the ground.

WATCH OUT — Two kinds of resistance. Some will argue AI dulls the force; others (often seasoned, less tech-savvy) are simply intimidated. Argument loses; a live demo on their own product wins both.

WATCH OUT — Single-point dependence. If you are the only one who knows the package, the rollout stops the day you are pulled away. Train at least one champion early — this is not optional.

WATCH OUT — Platform sharing gaps. Native sharing of personas and prompt libraries may be limited. Have a manual distribution method ready (a controlled reference doc / copy-paste package) so users are not blocked.

BE SURE TO — Keep the human in charge. The model never assigns Trained/Practiced/Untrained ratings and never gets the final word. The OCT owns the observation, the analyst validates, and every product is verified against doctrine before it goes forward.

BE SURE TO — Stay UNCLASSIFIED on NIPR. No classified information, no PII, no sensitive unit vulnerabilities go into the platform. When in doubt, generalize and scrub.

BE SURE TO — Measure your own before/after. Time a few products manually and AI-assisted at your unit; your own numbers convert skeptics and feed the division’s data. For reference, the division’s OSJ 2026 results: manual first-pass review caught only ~59% of errors (missed ~41%), experience barely predicted accuracy (Pearson r = 0.24), the modeled review-stage burden dropped ~97%, and measured live hands-on time was ~20.4 min per full CTO.

6.  Quick-Reference Card

Tear this out. The whole rollout on one page.

| Order of operations | License → onboard → train → employ. Never out of order. |
| --- | --- |
| Start now | Submit the license/token request a full training year before AT. |
| Find a wingman | Train 1–2 champions who are not you, early. |
| Sell by showing | Demonstrate on the user’s own product; never brief from slides. |
| Three-step method | Paste persona → paste task prompt → attach the document (drag-and-drop; no attach button). |
| Hard rules | UNCLASSIFIED / NIPR only. No PII. Verify against doctrine. No AI T/P/U ratings. |
| Before AT | Confirm tokens, refresh skills, dry-run the full cycle, distribute current personas/prompts. |
| Reach back | 84th Training Command AI Integration Working Group for licensing, tokens, and the package. |

Reference: Generative Artificial Intelligence Integration — Lessons and Best Practices Handbook (78th TD / 84th TC). This field guide operationalizes that handbook at battalion level.