EXECUTIVE SUMMARY Generative Artificial Intelligence Integration 78th Training Division │ 84th Training Command

| Prepared By: LTC Trey Waversak, 78th TD AI-Integrations Cell | Proponent: 84th TC AI Integration Working Group | Date: 18 June 2026 |
| --- | --- | --- |

BLUF. The 78th Training Division has fielded a proven, accredited generative AI capability (Ask Sage at IL5 / FedRAMP High) and measured its impact at Operation Sentinel Justice (OSJ) 2026. A controlled practical exercise established the manual baseline; throughput modeling projects a ~97% reduction in TAF review-stage processing burden and a ~58% compression of the end-to-end observation cycle. Early live employment data (N = 8) confirms real efficiency and quality gains while keeping a human verifier on every product. More than 300 personnel have been trained or reached. The capability is ready to scale. Decision required: approve institutionalization, enterprise licensing, command-wide expansion, and Phase 2 planning.

1.  THE PROBLEM

The JLLIS observation life cycle bottlenecks at the Training Analysis and Feedback (TAF) Tier 2 review. Under compressed exercise timelines, manual review of an observation’s narrative sections averaged 15.82 minutes per Command Training Objective (CTO) — an estimated ~24.8 minutes once analysts who reached the exercise time cap are counted — while missing roughly 41% of planted errors on first pass. Because the exercise scored only narrative sections (not Administrative Data or T&EO), these figures are a conservative floor. At OSJ scale (270 CTOs, 58 analysts), the manual process imposed an aggregate burden in the tens-to-low-hundreds of person-hours and compressed the time available to refine feedback to Rotational Training Units (RTUs) precisely when that feedback mattered most. The gap could not be closed by assigning more senior analysts: years of experience correlated only weakly with first-pass accuracy (Pearson 0.24). These conditions defined the problem the GenAI pilot was built to solve — and, as the results below show, did solve.

2.  THE SOLUTION

The 78th Training Division fielded a Divisional GenAI Package on Ask Sage (IL5 / FedRAMP High) — the only DoW-accredited platform employed. The package consists of three role-based AI personas (OCT, Chief OCT, TAF Analyst), a controlled prompt library, and standardized input templates. Employment follows a simple three-step method: paste the persona, paste the task prompt, attach the completed observation. The model extracts unit, task, date, and context automatically. Guardrails are embedded by design:

| No readiness ratings assigned | Human evaluators retain all T/P/U authority — the model never assigns ratings. |
| --- | --- |
| UNCLASSIFIED / NIPR only | No classified, PII, or sensitive vulnerability data is entered. |
| Verify before submitting | All AI-generated products are verified against current doctrine prior to submission. |
| Human authority retained | The OCT owns the observation; the analyst validates it; the model is decision support, never decision authority. |

3.  RESULTS

On 10 June 2026, during OSJ 2026 Control School training, MAJ Robert McDavid (78th TD AI-Integrations Cell) conducted a controlled practical exercise with 39 TAF Analysts (E6–O5), who reviewed a company-level JLLIS observation containing eight deliberate, scoreable errors under a 20-minute constraint. The exercise established the manual baseline; the projections below scale that baseline across the OSJ population.

| Measure (modeled projection) | Manual | AI-Assisted | Outcome |
| --- | --- | --- | --- |
| TAF review burden (270 CTOs) | ~115.9 hrs | ~3.25 hrs | ~97% reduction |
| End-to-end observation cycle | ~7.59 hrs | ~3.18 hrs | ~58% reduction |
| First-pass error detection | ~59% (4.69/8) | Strengthened | Catches what humans miss |
| Personnel trained / reached | — | 400+ | Demand-driven adoption |

Modeled projections. The ~97% figure isolates initial-pass processing within the TAF review stage; the ~58% figure spans the full life cycle. The two measure different things and are not additive.

Measured live employment (as of 18 June 2026). The first eight complete live reviews logged a Total Hands-On Time of 20.4 minutes per full CTO (~4.8 min AI interaction, ~15.6 min human verification). AI output graded 2 Ready, 4 Minor Edits, 2 Not Ready; analysts materially modified the AI product in 38% of reviews — evidence outputs were critically reviewed, not blindly accepted. On equalized full-CTO scope, this projects to roughly an 18% reduction against the adjusted manual baseline at current early-adoption proficiency. As the persona matures, measured performance is expected to move toward the modeled ceiling. The modeled and measured figures are different measurements, not competing claims.

4.  KEY LESSONS LEARNED

| License first | Token and licensing approval is the long pole in the tent — secure it before anything else. |
| --- | --- |
| Senior backing is decisive | A commander’s formal tasking converted a grassroots experiment into a resourced program. Rank unlocks institutional doors. |
| Exposure beats argument | Live demonstration overcame resistance that briefings could not. Seeing is believing. |
| Quality, not just speed | AI detects technical errors that experienced human analysts miss — a quality multiplier, not a shortcut. Publication and general/abbreviation errors are the highest-gap categories and the priority for persona optimization. |
| Build the AI Integration Cadre (AIIC) earlier | A two-person cell carried the entire effort. A deliberate, resourced champion cell would scale faster and reduce single-point fragility. |

5.  RESOURCING AND RISK

| Factor | Description | Assessment |
| --- | --- | --- |
| Primary cost driver | Enterprise license and token replenishment (recurring). | LOW — controlled, predictable |
| Risk if not resourced | Analyst overload at scale; degraded RTU product quality; unmanaged use of unaccredited tools. | HIGH — bottleneck returns |
| Controls in place | Human-in-the-loop authority; accredited platforms only; UNCLASSIFIED / NIPR; classification scrub on every product. | MITIGATED — by design |

6.  DECISIONS REQUIRED

| 1 | Institutionalize | Adopt the Divisional Package (personas, prompts, training, SOPs, data libraries) as a standing 78th Training Division product. |
| --- | --- | --- |
| 2 | Resource licensing | Fund enterprise licensing and token allocation — the recurring cost driver and precondition for all scale. |
| 3 | Authorize expansion | Direct expansion across the 84th TC and USARC over 12–24 months. |
| 4 | Approve Phase 2 | Authorize SIPR build-out planning, a deliberate AIIC cell, and evaluation of additional accredited tools. |

7.  RECOMMENDATION

APPROVE all four decisions and direct the 78th TD AI-Integrations Cell — supported by the 84th TC AI Integration Working Group — to execute. The capability is proven, trained, and ready. The limiting factor is resourcing and authority to scale.

References:  Generative Artificial Intelligence Integration — Lessons and Best Practices Handbook (78th TD, 2026); TAF Quality Control Performance Report — Manual vs. Ask Sage, OSJ 2026 (source for live Total Hands-On Time data).